Accreditation Standard Two

Turtle Timeline

8/3/11			Standard Two Turtle Groupings Identified

8/30/11		Key Communicators Confirmed

8/11/11 – 9/30/11	Training, Support Materials to Key Communicators

8/11/11 – 9/30/11	Turtle Membership finalized

10/10/11 – 10/21/11	Key Communicators hold Turtle organizational meetings

10/21/11 – 1/15/12	Turtle Teams meet, plan, and gather information

Suggested schedule is for Co-Leads to meet every two weeks for
			two hours, with full team meetings as needed

11/30/11 	Co-Leads and Key Communicators begin drafts of reports for team review

1/15/12	Initial Draft of Turtle reports shared with Turtle Partner and Accreditation Steering Committee

2/15/12	Final Draft of Turtle reports due to Accreditation Steering Committee

2/20/12	Accreditation Celebration/Appreciation/Feedback

3/30/12	Accreditation Steering Committee posts first draft of Standard Two report online for turtle-wide and all-campus feedback

3/30/12 – 4/30/12	Accreditation Steering Committee discusses report and gathers feedback from Expanded Presidents’ Council, College Council, VP meeting, etc.

5/15/12	Accreditation Steering Committee posts second draft of Standard Two report online for turtle-wide and all-campus feedback

5/15/12 – 6/15/12	Accreditation Steering Committee discusses report and gathers feedback from Expanded Presidents’ Council, College Council, VP meeting, etc.

6/15/12 – 9/1/12	Accreditation Steering Committee finalizes documents and submits to NWCCU.