CCC Strategic Planning for Enrollment Management

Project Timeline – Final Draft

| Task | Lead/Support | Date | Status |
| --- | --- | --- | --- |
| Present SEM proposal to the Executive Team | Diane, Bill Z., and Shelly P. | December 4, 2007 | Completed |
| Share SEM proposal with Presidents Council and Joint Deans | Diane, Bill Z. and Shelly P. | December 11, 2007 | Completed |
| Finalize project scope and consulting agreements with AACRAO and Willis & Green Associates | Diane, Exec. Team | January 11, 2008 | In Progress |
| Establish project timeline | Diane, Bill Z. and Shelly P. | January 11, 2008 | Completed |
| Determine SEM committee membership | Diane, Bill Z., and Shelly P., Expanded Presidents Council, Joint Deans | January 18 – April 3 | In progress |
| Share SEM project plan and timeline with Exec. Team, Expanded Presidents Council and College Council | Diane, Bill Z. and Shelly P. | January 18, 2008 |  |
| Pre-visit materials delivered for first AACRAO visit | Diane and Shelly P. | January 22, 2008 |  |
| Pre-visit phone conference with AACRAO consultants | Diane, Bill Z. and Shelly P. | January 25, 2008 |  |
| First AACRAO visit | Diane, Bill Z., Shelly P., Outreach, Enrollment Services, Academic Advising and Marketing Expanded Presidents Council, Joint Deans and Prime Time Team | January 28, 2008 January 29, 2008 |  |
| Pre-visit phone conference with AACRAO consultants | Diane, Bill Z., Shelly P. | February 13, 2008 |  |
| Second AACRAO visit | Diane, Bill Z., Shelly P., and project team Diane, Bill Z., Shelly P., present AACRAO consultants at VP Meeting | February 14, 2008 February 15, 2008 |  |
| Pre-visit phone conference with AACRAO consultant | Diane, Bill Z., Shelly P. | March 6, 2008 |  |
| Third – final AACRAO visit | Diane, Bill Z., Shelly P., full SEM project team, Connie Green, and other interested college community members | March 7, 2008 |  |
| SEM committee planning meetings with Willis & Green (phone conference or on site as needed) | Diane, Bill Z., Shelly P. and Connie Green | March 14, 28 April 7, 25 May 9, 2008 |  |
| SEM Committee Kick Off | Diane, Bill Z., Shelly P, Connie Green and SEM Committee members | April 3, 2008 |  |

Project Leads:  			Diane Drebin, Bill Zuelke, Shelly Parini

CCC SEM Project Team:  	Prime Time Enrollment Strategies team members, Expanded Presidents Council, College Council

CCC SEM Committtee: 	To be determined

L:SEMProject010808