## Slide 1: Update: InSS Evaluation and Design
Presented March 1, 2024

## Slide 2: Resources
Moodle Site for Evaluation and Design Project
FAQs
Timeline
InSS organizational chart
Listening stage results
Anonymous suggestion box

## Slide 3: Progress
Listening Stage – Activities:
InSS employee survey
InSS employee open forums
Interviews with comparable institutions
InSS employee focus groups

## Slide 4: Next steps – Winter
Synthesis Stage
InSS Deans draft a synthesis of all listening products
Review with impacted areas
Share with CCC stakeholders
Core design team (advisory group +) finalizes synthesis

## Slide 5: Next steps – Spring
Design stage:
Core Design team (split into 3 separate subgroups) builds scenarios (3) based on synthesis
Comment stage:
Scenarios shared with college community for input
Project leads (InSS Deans) recommend changes
Executive Team makes decision about changes in structure

## Slide 6: Next steps Summer 24 – Spring 25
Phase 1 – Structure completed:
Implementation of structural changes – beginning fall 2024 through spring 2026, depending on scope of change
Phase 2 – Roles and responsibilities:
Process planning in Summer 2024
Similar phases – listening, synthesis and design, comment, decision

## Slide 7: Questions?